## Phase 1 - Unity 3D AR
SciLab: Phase 1 Standalone Unity 3D AR Development & Proposal Defense
Pre-Sprint Setup, Core AR Engine, Experiments 1–6, and Academic Proposal Defense (Sep 2025 – Jul 2026)
SPRINT / ACTIVITY & TASKS | SEP 2025 |  |  |  | OCT 2025 |  |  |  | NOV 2025 |  |  |  | DEC 2025 |  |  |  | JAN 2026 |  |  |  | FEB 2026 |  |  |  | MAR 2026 |  |  |  | JUN 2026 |  |  |  | JUL 2026 |  |  |  | STATUS | KEY DELIVERABLES AND ACCOMPLISHMENTS
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
PRE-SPRINT: INCEPTION & ENVIRONMENT SETUP (SEPTEMBER 2025)
Problem Identification & Initial Setup | ■ | ■ | ■ | ■ | [32 empty] | COMPLETED | Conducted preliminary research, identified high school chemistry lab safety/resource limitations, and established Unity 3D AR project baseline.
Curriculum Alignment & Syllabus Mapping | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | [28 empty] | COMPLETED | Mapped target Philippine science curriculum competencies to 7 core laboratory experiments and atomic theory topics.
3D Laboratory Asset Modeling & Texturing |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | [26 empty] | COMPLETED | Modeled custom 3D laboratory apparatus (beakers, Erlenmeyer flasks, test tubes, Bunsen burner, digital scale, copper electrodes, wires).
SPRINT 1: CORE AR ENGINE & TRACKING PIPELINE (OCTOBER – NOVEMBER 2025)
Sprint Planning | [5 empty] | ■ | ■ | [29 empty] | COMPLETED | Defined technical scope for plane tracking, camera feed integration, and Vuforia SDK licensing/setup.
Core AR Engine & Vuforia SDK Setup | [6 empty] | ■ | ■ | ■ | ■ | ■ | [25 empty] | COMPLETED | Configured Vuforia image target recognition, coordinate tracking, camera permissions, and real-world scale calibration.
Asset Integration & Interaction Logic | [6 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | [23 empty] | COMPLETED | Engineered physical gesture manipulations (LeanTouch drag, rotate, inspect) and initial collision boundary detection.
System Review Loop | [10 empty] | ■ | ■ | [24 empty] | COMPLETED | Evaluated tracking stability across varied classroom lighting, surface glare, and device camera resolutions.
SPRINT 2: EXPERIMENT 1 – ELEPHANT TOOTHPASTE (DECEMBER 2025 – JANUARY 2026)
Sprint Planning | [11 empty] | ■ | [24 empty] | COMPLETED | Decomposed catalytic decomposition reaction into milestone user steps and visual particle triggers.
UI/UX View Layout & Guidance Prompts | [12 empty] | ■ | ■ | ■ | ■ | ■ | ■ | [18 empty] | COMPLETED | Designed in-game HUD, floating reaction guide prompts, and dynamic ingredient interaction cues.
Engine Familiarization & Interaction Physics | [12 empty] | ■ | ■ | ■ | ■ | ■ | ■ | [18 empty] | COMPLETED | Simulated multi-fluid pouring kinematics and potassium iodide catalyst triggers for H2O2 breakdown.
Tracking Stability Verification | [14 empty] | ■ | ■ | ■ | ■ | [18 empty] | COMPLETED | Verified zero-drift foam particle system expansion and continuous anchor tracking during intense VFX.
System Review Loop | [14 empty] | ■ | ■ | ■ | ■ | [18 empty] | COMPLETED | Conducted functional playthroughs, refined collision boundaries, and tuned foam expansion scaling.
SPRINT 3: EXPERIMENTS 2 & 3 – PRECIPITATION & GAS EVOLUTION (DECEMBER 2025 – JANUARY 2026)
Sprint Planning (Basic Simulations) | [13 empty] | ■ | ■ | [21 empty] | COMPLETED | Organized backlog for Exp 2 (Silver Nitrate + NaCl precipitate) and Exp 3 (Limewater CO2 gas evolution).
Asset Integration (3D Models & Glassware) | [13 empty] | ■ | ■ | ■ | ■ | ■ | ■ | [17 empty] | COMPLETED | Modeled custom dropper pipette, test tube rack, delivery gas tube, and Erlenmeyer reaction flask.
Accelerated Integration (Remaining Basic Models) | [13 empty] | ■ | ■ | ■ | ■ | ■ | ■ | [17 empty] | COMPLETED | Applied established pouring and liquid color-shift shader pipeline to expedite dual-experiment assembly.
System Review Loop (Exp 2 & Exp 3) | [13 empty] | ■ | ■ | ■ | ■ | [19 empty] | COMPLETED | Validated instant white AgCl precipitate appearance and milky white CaCO3 turbidity animation under delivery tube flow.
SPRINT 4: EXPERIMENTS 4, 5, 6 & PROPOSAL DEFENSE (FEBRUARY – JULY 2026)
Sprint Planning (Complex Modules & Editors) | [20 empty] | ■ | ■ | [14 empty] | COMPLETED | Organized backlog for complex modules: atomic flame emission spectra, closed-system mass balance, and electrical conductivity.
Content Validation (Science Department Faculty) | [21 empty] | ■ | ■ | ■ | ■ | ■ | [10 empty] | COMPLETED | Formal pedagogical and scientific validation strictly by science department faculty members for physical reaction accuracy.
Advanced Simulation (Exp 4 Flame, Exp 5, Exp 6) | [20 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | [9 empty] | COMPLETED | Developed full simulation and reaction VFX: Bunsen burner flame test colors (Cu, Ba, Sr, Na, K, Li, Ca), circuit electrolyte testing, and sealed balloon mass conservation.
System Review Loop (Academic Proposal Defense) | [20 empty] | ■ | ■ | ■ | ■ |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | COMPLETED | Chapter 1–3 Proposal Defense successfully completed; system verified at 90% completion in Unity AR; established strategic necessity to pivot to Flutter for native mobile LMS.

## Phase 2 - Flutter LMS & Safety
SciLab: Phase 2 Flutter LMS Ecosystem, AR Embedding & Chemical Safety
Multi-Role Architecture, Firestore API, unityLibrary Embedding, 3D Periodic Table & Safety Engine (Aug 2026 – Oct 2026 Present)
SPRINT / ACTIVITY & TASKS | AUG 2026 |  |  |  | SEP 2026 |  |  |  | OCT 2026 |  |  |  | STATUS | KEY DELIVERABLES AND ACCOMPLISHMENTS
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
SPRINT 5: LMS ECOSYSTEM, CLOUD ARCHITECTURE & UAAL EVALUATION (AUGUST 2026)
LMS Ecosystem and Role Architecture | ■ | ■ | [10 empty] | COMPLETED | Designed multi-role architecture separating Student (mobile AR), Teacher (web/mobile class management), and Admin (system governance).
Cloud Database & API Schema Design (Firestore) |  | ■ | ■ | [9 empty] | COMPLETED | Architected Cloud Firestore collections: user profiles, sections, dynamic lab steps, quiz submissions, and activity audit logs.
Unity-as-a-Library (UaaL) Feasibility & Bridge Design |  | ■ | ■ | ■ | [8 empty] | COMPLETED | Investigated and verified UaaL integration using flutter_unity_widget; mapped asynchronous C# <-> Dart messaging contract.
Flutter Core App Setup & SciLab Neon Design System | ■ | ■ | [10 empty] | COMPLETED | Initialized Flutter project, established AppTheme with neon cyan/emerald palette, responsive layouts, and Google Fonts typography.
Authentication & Teacher Verification Queue | ■ | ■ | ■ | [9 empty] | COMPLETED | Implemented Firebase Auth (Email/Password, Google Sign-in) and teacher account approval workflow with pending state gates.
Student & Teacher Portal Core Development |  | ■ | ■ | ■ | [8 empty] | COMPLETED | Built Student Course Hub, offline experiment fallback steps, Teacher Section management, and student enrollment dialogs.
Admin Web Portal Deployment (Firebase Hosting) |  |  | ■ | ■ | [8 empty] | COMPLETED | Deployed responsive Admin Web application on Firebase Hosting for platform-wide user moderation, section oversight, and content audits.
Multimedia Storage & In-App Viewers Suite |  |  | ■ | ■ | [8 empty] | COMPLETED | Integrated Firebase Storage and built native PDF viewer, video player with custom controls, and image zoom modal.
AI Quiz Generator & YouTube Lesson Integration |  | ■ | ■ | ■ | [8 empty] | COMPLETED | Built AI quiz generator module for automated assessment creation and curated YouTube educational video embed feed.
SPRINT 6: AR EMBEDDING, EXPERIMENT 7 & UI/UX REDESIGN (SEPTEMBER 2026)
Unity Android Export & unityLibrary Integration |  |  |  |  | ■ | ■ | [6 empty] | COMPLETED | Exported Unity 3D engine to native Android unityLibrary (arm64-v8a) and integrated into Flutter Gradle build pipeline.
Bidirectional C# <-> Dart Communication Bridge |  |  |  |  | ■ | ■ | ■ | [5 empty] | COMPLETED | Implemented FlutterReceiver.cs and SendToFlutter.cs bridge for realtime step triggers, score sync, and error handling.
Unity Canvas UI Elimination & Flutter Overlay Redesign | [5 empty] | ■ | ■ | ■ |  |  |  |  | COMPLETED | Removed clunky Unity legacy Canvas UI; created sleek Flutter native overlay cards, animated step progress, and back navigation.
Experiment 7: pH Indicator Acid & Base Reaction Setup | [5 empty] | ■ | ■ | [5 empty] | COMPLETED | Integrated household acid-base chemical reactions (Bleach, Lemon Juice, Soap, Water, Blood) with dynamic liquid shader color transitions.
Dynamic Firestore AR Steps & Offline Fallback Engine | [6 empty] | ■ | ■ |  |  |  |  | COMPLETED | Implemented teacher-editable AR steps synced via Firestore with automatic zero-lag fallback to hardcoded instructions when offline.
Teacher Analytics, Searchable IDs & Needs Help Filter | [5 empty] | ■ | ■ | ■ |  |  |  |  | COMPLETED | Added class average scoring cards, searchable student IDs, and one-touch 'Needs Help' filter to spotlight struggling students.
SPRINT 7: PERIODIC TABLE, ADVANCED LAB SIMULATION & SAFETY (OCTOBER 2026 – PRESENT)
3D Interactive Periodic Table of Elements (Created in October) | [8 empty] | ■ | ■ |  |  | COMPLETED | Engineered AR 3D interactive periodic table with category color coding, orbital shell visualization, and comprehensive element data drawer.
Responsive Flame Test Solution Picker Dialog | [8 empty] | ■ | ■ |  |  | COMPLETED | Redesigned solution picker modal matching SciLab aesthetics; resolved RenderFlex overflow issues across landscape and compact mobile screens.
Order-Independent Flexible Ingredient Mixing Engine | [8 empty] | ■ | ■ |  |  | COMPLETED | Overhauled reaction logic across Exp 1 to Exp 6 to allow ingredients to be mixed in any order prior to activator addition (preserving strict steps for Exp 7 & 8).
Chemical Safety Hazard Warning Engine (Toxic Gas Modal) | [9 empty] | ■ |  |  | ACTIVE / POLISHED | Implemented high-visibility safety hazard modal with 'OK' dismissal and instant scene reset upon lethal chemical mixes (e.g., Bleach + Acid -> Cl2 gas).
Universal Light & Dark Mode Theming Across All Views | [8 empty] | ■ | ■ |  |  | COMPLETED | Implemented complete dual-theme palette across Student, Teacher, and Web Admin interfaces with dynamic persistent preference caching.

## Full End-to-End Timeline
SciLab: Complete End-to-End Project Gantt Chart (Sep 2025 – Oct 2026 Present)
Complete Master Roadmap: Pure Unity 3D AR Engine + Proposal Defense + Multi-Role Flutter LMS + AR Safety Engine
SPRINT / ACTIVITY & TASKS | SEP 2025 |  |  |  | OCT 2025 |  |  |  | NOV 2025 |  |  |  | DEC 2025 |  |  |  | JAN 2026 |  |  |  | FEB 2026 |  |  |  | MAR 2026 |  |  |  | JUN 2026 |  |  |  | JUL 2026 |  |  |  | AUG 2026 |  |  |  | SEP 2026 |  |  |  | OCT 2026 |  |  |  | STATUS | KEY DELIVERABLES AND ACCOMPLISHMENTS
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
PRE-SPRINT: INCEPTION & ENVIRONMENT SETUP (SEPTEMBER 2025)
Problem Identification & Initial Setup | ■ | ■ | ■ | ■ | [44 empty] | COMPLETED | Conducted preliminary research, identified high school chemistry lab safety/resource limitations, and established Unity 3D AR project baseline.
Curriculum Alignment & Syllabus Mapping | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | [40 empty] | COMPLETED | Mapped target Philippine science curriculum competencies to 7 core laboratory experiments and atomic theory topics.
3D Laboratory Asset Modeling & Texturing |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | [38 empty] | COMPLETED | Modeled custom 3D laboratory apparatus (beakers, Erlenmeyer flasks, test tubes, Bunsen burner, digital scale, copper electrodes, wires).
SPRINT 1: CORE AR ENGINE & TRACKING PIPELINE (OCTOBER – NOVEMBER 2025)
Sprint Planning | [5 empty] | ■ | ■ | [41 empty] | COMPLETED | Defined technical scope for plane tracking, camera feed integration, and Vuforia SDK licensing/setup.
Core AR Engine & Vuforia SDK Setup | [6 empty] | ■ | ■ | ■ | ■ | ■ | [37 empty] | COMPLETED | Configured Vuforia image target recognition, coordinate tracking, camera permissions, and real-world scale calibration.
Asset Integration & Interaction Logic | [6 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | [35 empty] | COMPLETED | Engineered physical gesture manipulations (LeanTouch drag, rotate, inspect) and initial collision boundary detection.
System Review Loop | [10 empty] | ■ | ■ | [36 empty] | COMPLETED | Evaluated tracking stability across varied classroom lighting, surface glare, and device camera resolutions.
SPRINT 2: EXPERIMENT 1 – ELEPHANT TOOTHPASTE (DECEMBER 2025 – JANUARY 2026)
Sprint Planning | [11 empty] | ■ | [36 empty] | COMPLETED | Decomposed catalytic decomposition reaction into milestone user steps and visual particle triggers.
UI/UX View Layout & Guidance Prompts | [12 empty] | ■ | ■ | ■ | ■ | ■ | ■ | [30 empty] | COMPLETED | Designed in-game HUD, floating reaction guide prompts, and dynamic ingredient interaction cues.
Engine Familiarization & Interaction Physics | [12 empty] | ■ | ■ | ■ | ■ | ■ | ■ | [30 empty] | COMPLETED | Simulated multi-fluid pouring kinematics and potassium iodide catalyst triggers for H2O2 breakdown.
Tracking Stability Verification | [14 empty] | ■ | ■ | ■ | ■ | [30 empty] | COMPLETED | Verified zero-drift foam particle system expansion and continuous anchor tracking during intense VFX.
System Review Loop | [14 empty] | ■ | ■ | ■ | ■ | [30 empty] | COMPLETED | Conducted functional playthroughs, refined collision boundaries, and tuned foam expansion scaling.
SPRINT 3: EXPERIMENTS 2 & 3 – PRECIPITATION & GAS EVOLUTION (DECEMBER 2025 – JANUARY 2026)
Sprint Planning (Basic Simulations) | [13 empty] | ■ | ■ | [33 empty] | COMPLETED | Organized backlog for Exp 2 (Silver Nitrate + NaCl precipitate) and Exp 3 (Limewater CO2 gas evolution).
Asset Integration (3D Models & Glassware) | [13 empty] | ■ | ■ | ■ | ■ | ■ | ■ | [29 empty] | COMPLETED | Modeled custom dropper pipette, test tube rack, delivery gas tube, and Erlenmeyer reaction flask.
Accelerated Integration (Remaining Basic Models) | [13 empty] | ■ | ■ | ■ | ■ | ■ | ■ | [29 empty] | COMPLETED | Applied established pouring and liquid color-shift shader pipeline to expedite dual-experiment assembly.
System Review Loop (Exp 2 & Exp 3) | [13 empty] | ■ | ■ | ■ | ■ | [31 empty] | COMPLETED | Validated instant white AgCl precipitate appearance and milky white CaCO3 turbidity animation under delivery tube flow.
SPRINT 4: EXPERIMENTS 4, 5, 6 & PROPOSAL DEFENSE (FEBRUARY – JULY 2026)
Sprint Planning (Complex Modules & Editors) | [20 empty] | ■ | ■ | [26 empty] | COMPLETED | Organized backlog for complex modules: atomic flame emission spectra, closed-system mass balance, and electrical conductivity.
Content Validation (Science Department Faculty) | [21 empty] | ■ | ■ | ■ | ■ | ■ | [22 empty] | COMPLETED | Formal pedagogical and scientific validation strictly by science department faculty members for physical reaction accuracy.
Advanced Simulation (Exp 4 Flame, Exp 5, Exp 6) | [20 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■ | [21 empty] | COMPLETED | Developed full simulation and reaction VFX: Bunsen burner flame test colors (Cu, Ba, Sr, Na, K, Li, Ca), circuit electrolyte testing, and sealed balloon mass conservation.
System Review Loop (Academic Proposal Defense) | [20 empty] | ■ | ■ | ■ | ■ |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | [12 empty] | COMPLETED | Chapter 1–3 Proposal Defense successfully completed; system verified at 90% completion in Unity AR; established strategic necessity to pivot to Flutter for native mobile LMS.
SPRINT 5: LMS ECOSYSTEM, CLOUD ARCHITECTURE & UAAL EVALUATION (AUGUST 2026)
LMS Ecosystem and Role Architecture | [36 empty] | ■ | ■ | [10 empty] | COMPLETED | Designed multi-role architecture separating Student (mobile AR), Teacher (web/mobile class management), and Admin (system governance).
Cloud Database & API Schema Design (Firestore) | [37 empty] | ■ | ■ | [9 empty] | COMPLETED | Architected Cloud Firestore collections: user profiles, sections, dynamic lab steps, quiz submissions, and activity audit logs.
Unity-as-a-Library (UaaL) Feasibility & Bridge Design | [37 empty] | ■ | ■ | ■ | [8 empty] | COMPLETED | Investigated and verified UaaL integration using flutter_unity_widget; mapped asynchronous C# <-> Dart messaging contract.
Flutter Core App Setup & SciLab Neon Design System | [36 empty] | ■ | ■ | [10 empty] | COMPLETED | Initialized Flutter project, established AppTheme with neon cyan/emerald palette, responsive layouts, and Google Fonts typography.
Authentication & Teacher Verification Queue | [36 empty] | ■ | ■ | ■ | [9 empty] | COMPLETED | Implemented Firebase Auth (Email/Password, Google Sign-in) and teacher account approval workflow with pending state gates.
Student & Teacher Portal Core Development | [37 empty] | ■ | ■ | ■ | [8 empty] | COMPLETED | Built Student Course Hub, offline experiment fallback steps, Teacher Section management, and student enrollment dialogs.
Admin Web Portal Deployment (Firebase Hosting) | [38 empty] | ■ | ■ | [8 empty] | COMPLETED | Deployed responsive Admin Web application on Firebase Hosting for platform-wide user moderation, section oversight, and content audits.
Multimedia Storage & In-App Viewers Suite | [38 empty] | ■ | ■ | [8 empty] | COMPLETED | Integrated Firebase Storage and built native PDF viewer, video player with custom controls, and image zoom modal.
AI Quiz Generator & YouTube Lesson Integration | [37 empty] | ■ | ■ | ■ | [8 empty] | COMPLETED | Built AI quiz generator module for automated assessment creation and curated YouTube educational video embed feed.
SPRINT 6: AR EMBEDDING, EXPERIMENT 7 & UI/UX REDESIGN (SEPTEMBER 2026)
Unity Android Export & unityLibrary Integration | [40 empty] | ■ | ■ | [6 empty] | COMPLETED | Exported Unity 3D engine to native Android unityLibrary (arm64-v8a) and integrated into Flutter Gradle build pipeline.
Bidirectional C# <-> Dart Communication Bridge | [40 empty] | ■ | ■ | ■ | [5 empty] | COMPLETED | Implemented FlutterReceiver.cs and SendToFlutter.cs bridge for realtime step triggers, score sync, and error handling.
Unity Canvas UI Elimination & Flutter Overlay Redesign | [41 empty] | ■ | ■ | ■ |  |  |  |  | COMPLETED | Removed clunky Unity legacy Canvas UI; created sleek Flutter native overlay cards, animated step progress, and back navigation.
Experiment 7: pH Indicator Acid & Base Reaction Setup | [41 empty] | ■ | ■ | [5 empty] | COMPLETED | Integrated household acid-base chemical reactions (Bleach, Lemon Juice, Soap, Water, Blood) with dynamic liquid shader color transitions.
Dynamic Firestore AR Steps & Offline Fallback Engine | [42 empty] | ■ | ■ |  |  |  |  | COMPLETED | Implemented teacher-editable AR steps synced via Firestore with automatic zero-lag fallback to hardcoded instructions when offline.
Teacher Analytics, Searchable IDs & Needs Help Filter | [41 empty] | ■ | ■ | ■ |  |  |  |  | COMPLETED | Added class average scoring cards, searchable student IDs, and one-touch 'Needs Help' filter to spotlight struggling students.
SPRINT 7: PERIODIC TABLE, ADVANCED LAB SIMULATION & SAFETY (OCTOBER 2026 – PRESENT)
3D Interactive Periodic Table of Elements (Created in October) | [44 empty] | ■ | ■ |  |  | COMPLETED | Engineered AR 3D interactive periodic table with category color coding, orbital shell visualization, and comprehensive element data drawer.
Responsive Flame Test Solution Picker Dialog | [44 empty] | ■ | ■ |  |  | COMPLETED | Redesigned solution picker modal matching SciLab aesthetics; resolved RenderFlex overflow issues across landscape and compact mobile screens.
Order-Independent Flexible Ingredient Mixing Engine | [44 empty] | ■ | ■ |  |  | COMPLETED | Overhauled reaction logic across Exp 1 to Exp 6 to allow ingredients to be mixed in any order prior to activator addition (preserving strict steps for Exp 7 & 8).
Chemical Safety Hazard Warning Engine (Toxic Gas Modal) | [45 empty] | ■ |  |  | ACTIVE / POLISHED | Implemented high-visibility safety hazard modal with 'OK' dismissal and instant scene reset upon lethal chemical mixes (e.g., Bleach + Acid -> Cl2 gas).
Universal Light & Dark Mode Theming Across All Views | [44 empty] | ■ | ■ |  |  | COMPLETED | Implemented complete dual-theme palette across Student, Teacher, and Web Admin interfaces with dynamic persistent preference caching.

## Phase 1 (Printable Light)
SciLab: Phase 1 Standalone Unity 3D AR Development & Proposal Defense
Pre-Sprint Setup, Core AR Engine, Experiments 1–6, and Academic Proposal Defense (Sep 2025 – Jul 2026)
SPRINT / ACTIVITY & TASKS | SEP 2025 |  |  |  | OCT 2025 |  |  |  | NOV 2025 |  |  |  | DEC 2025 |  |  |  | JAN 2026 |  |  |  | FEB 2026 |  |  |  | MAR 2026 |  |  |  | JUN 2026 |  |  |  | JUL 2026 |  |  |  | STATUS | KEY DELIVERABLES AND ACCOMPLISHMENTS
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
PRE-SPRINT: INCEPTION & ENVIRONMENT SETUP (SEPTEMBER 2025)
Problem Identification & Initial Setup | ✔ | ✔ | ✔ | ✔ | [32 empty] | COMPLETED | Conducted preliminary research, identified high school chemistry lab safety/resource limitations, and established Unity 3D AR project baseline.
Curriculum Alignment & Syllabus Mapping | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | [28 empty] | COMPLETED | Mapped target Philippine science curriculum competencies to 7 core laboratory experiments and atomic theory topics.
3D Laboratory Asset Modeling & Texturing |  |  |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | [26 empty] | COMPLETED | Modeled custom 3D laboratory apparatus (beakers, Erlenmeyer flasks, test tubes, Bunsen burner, digital scale, copper electrodes, wires).
SPRINT 1: CORE AR ENGINE & TRACKING PIPELINE (OCTOBER – NOVEMBER 2025)
Sprint Planning | [5 empty] | ✔ | ✔ | [29 empty] | COMPLETED | Defined technical scope for plane tracking, camera feed integration, and Vuforia SDK licensing/setup.
Core AR Engine & Vuforia SDK Setup | [6 empty] | ✔ | ✔ | ✔ | ✔ | ✔ | [25 empty] | COMPLETED | Configured Vuforia image target recognition, coordinate tracking, camera permissions, and real-world scale calibration.
Asset Integration & Interaction Logic | [6 empty] | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | [23 empty] | COMPLETED | Engineered physical gesture manipulations (LeanTouch drag, rotate, inspect) and initial collision boundary detection.
System Review Loop | [10 empty] | ✔ | ✔ | [24 empty] | COMPLETED | Evaluated tracking stability across varied classroom lighting, surface glare, and device camera resolutions.
SPRINT 2: EXPERIMENT 1 – ELEPHANT TOOTHPASTE (DECEMBER 2025 – JANUARY 2026)
Sprint Planning | [11 empty] | ✔ | [24 empty] | COMPLETED | Decomposed catalytic decomposition reaction into milestone user steps and visual particle triggers.
UI/UX View Layout & Guidance Prompts | [12 empty] | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | [18 empty] | COMPLETED | Designed in-game HUD, floating reaction guide prompts, and dynamic ingredient interaction cues.
Engine Familiarization & Interaction Physics | [12 empty] | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | [18 empty] | COMPLETED | Simulated multi-fluid pouring kinematics and potassium iodide catalyst triggers for H2O2 breakdown.
Tracking Stability Verification | [14 empty] | ✔ | ✔ | ✔ | ✔ | [18 empty] | COMPLETED | Verified zero-drift foam particle system expansion and continuous anchor tracking during intense VFX.
System Review Loop | [14 empty] | ✔ | ✔ | ✔ | ✔ | [18 empty] | COMPLETED | Conducted functional playthroughs, refined collision boundaries, and tuned foam expansion scaling.
SPRINT 3: EXPERIMENTS 2 & 3 – PRECIPITATION & GAS EVOLUTION (DECEMBER 2025 – JANUARY 2026)
Sprint Planning (Basic Simulations) | [13 empty] | ✔ | ✔ | [21 empty] | COMPLETED | Organized backlog for Exp 2 (Silver Nitrate + NaCl precipitate) and Exp 3 (Limewater CO2 gas evolution).
Asset Integration (3D Models & Glassware) | [13 empty] | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | [17 empty] | COMPLETED | Modeled custom dropper pipette, test tube rack, delivery gas tube, and Erlenmeyer reaction flask.
Accelerated Integration (Remaining Basic Models) | [13 empty] | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | [17 empty] | COMPLETED | Applied established pouring and liquid color-shift shader pipeline to expedite dual-experiment assembly.
System Review Loop (Exp 2 & Exp 3) | [13 empty] | ✔ | ✔ | ✔ | ✔ | [19 empty] | COMPLETED | Validated instant white AgCl precipitate appearance and milky white CaCO3 turbidity animation under delivery tube flow.
SPRINT 4: EXPERIMENTS 4, 5, 6 & PROPOSAL DEFENSE (FEBRUARY – JULY 2026)
Sprint Planning (Complex Modules & Editors) | [20 empty] | ✔ | ✔ | [14 empty] | COMPLETED | Organized backlog for complex modules: atomic flame emission spectra, closed-system mass balance, and electrical conductivity.
Content Validation (Science Department Faculty) | [21 empty] | ✔ | ✔ | ✔ | ✔ | ✔ | [10 empty] | COMPLETED | Formal pedagogical and scientific validation strictly by science department faculty members for physical reaction accuracy.
Advanced Simulation (Exp 4 Flame, Exp 5, Exp 6) | [20 empty] | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | [9 empty] | COMPLETED | Developed full simulation and reaction VFX: Bunsen burner flame test colors (Cu, Ba, Sr, Na, K, Li, Ca), circuit electrolyte testing, and sealed balloon mass conservation.
System Review Loop (Academic Proposal Defense) | [20 empty] | ✔ | ✔ | ✔ | ✔ |  |  |  |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | COMPLETED | Chapter 1–3 Proposal Defense successfully completed; system verified at 90% completion in Unity AR; established strategic necessity to pivot to Flutter for native mobile LMS.

## Phase 2 (Printable Light)
SciLab: Phase 2 Flutter LMS Ecosystem, AR Embedding & Chemical Safety
Multi-Role Architecture, Firestore API, unityLibrary Embedding, 3D Periodic Table & Safety Engine (Aug 2026 – Oct 2026 Present)
SPRINT / ACTIVITY & TASKS | AUG 2026 |  |  |  | SEP 2026 |  |  |  | OCT 2026 |  |  |  | STATUS | KEY DELIVERABLES AND ACCOMPLISHMENTS
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
SPRINT 5: LMS ECOSYSTEM, CLOUD ARCHITECTURE & UAAL EVALUATION (AUGUST 2026)
LMS Ecosystem and Role Architecture | ✔ | ✔ | [10 empty] | COMPLETED | Designed multi-role architecture separating Student (mobile AR), Teacher (web/mobile class management), and Admin (system governance).
Cloud Database & API Schema Design (Firestore) |  | ✔ | ✔ | [9 empty] | COMPLETED | Architected Cloud Firestore collections: user profiles, sections, dynamic lab steps, quiz submissions, and activity audit logs.
Unity-as-a-Library (UaaL) Feasibility & Bridge Design |  | ✔ | ✔ | ✔ | [8 empty] | COMPLETED | Investigated and verified UaaL integration using flutter_unity_widget; mapped asynchronous C# <-> Dart messaging contract.
Flutter Core App Setup & SciLab Neon Design System | ✔ | ✔ | [10 empty] | COMPLETED | Initialized Flutter project, established AppTheme with neon cyan/emerald palette, responsive layouts, and Google Fonts typography.
Authentication & Teacher Verification Queue | ✔ | ✔ | ✔ | [9 empty] | COMPLETED | Implemented Firebase Auth (Email/Password, Google Sign-in) and teacher account approval workflow with pending state gates.
Student & Teacher Portal Core Development |  | ✔ | ✔ | ✔ | [8 empty] | COMPLETED | Built Student Course Hub, offline experiment fallback steps, Teacher Section management, and student enrollment dialogs.
Admin Web Portal Deployment (Firebase Hosting) |  |  | ✔ | ✔ | [8 empty] | COMPLETED | Deployed responsive Admin Web application on Firebase Hosting for platform-wide user moderation, section oversight, and content audits.
Multimedia Storage & In-App Viewers Suite |  |  | ✔ | ✔ | [8 empty] | COMPLETED | Integrated Firebase Storage and built native PDF viewer, video player with custom controls, and image zoom modal.
AI Quiz Generator & YouTube Lesson Integration |  | ✔ | ✔ | ✔ | [8 empty] | COMPLETED | Built AI quiz generator module for automated assessment creation and curated YouTube educational video embed feed.
SPRINT 6: AR EMBEDDING, EXPERIMENT 7 & UI/UX REDESIGN (SEPTEMBER 2026)
Unity Android Export & unityLibrary Integration |  |  |  |  | ✔ | ✔ | [6 empty] | COMPLETED | Exported Unity 3D engine to native Android unityLibrary (arm64-v8a) and integrated into Flutter Gradle build pipeline.
Bidirectional C# <-> Dart Communication Bridge |  |  |  |  | ✔ | ✔ | ✔ | [5 empty] | COMPLETED | Implemented FlutterReceiver.cs and SendToFlutter.cs bridge for realtime step triggers, score sync, and error handling.
Unity Canvas UI Elimination & Flutter Overlay Redesign | [5 empty] | ✔ | ✔ | ✔ |  |  |  |  | COMPLETED | Removed clunky Unity legacy Canvas UI; created sleek Flutter native overlay cards, animated step progress, and back navigation.
Experiment 7: pH Indicator Acid & Base Reaction Setup | [5 empty] | ✔ | ✔ | [5 empty] | COMPLETED | Integrated household acid-base chemical reactions (Bleach, Lemon Juice, Soap, Water, Blood) with dynamic liquid shader color transitions.
Dynamic Firestore AR Steps & Offline Fallback Engine | [6 empty] | ✔ | ✔ |  |  |  |  | COMPLETED | Implemented teacher-editable AR steps synced via Firestore with automatic zero-lag fallback to hardcoded instructions when offline.
Teacher Analytics, Searchable IDs & Needs Help Filter | [5 empty] | ✔ | ✔ | ✔ |  |  |  |  | COMPLETED | Added class average scoring cards, searchable student IDs, and one-touch 'Needs Help' filter to spotlight struggling students.
SPRINT 7: PERIODIC TABLE, ADVANCED LAB SIMULATION & SAFETY (OCTOBER 2026 – PRESENT)
3D Interactive Periodic Table of Elements (Created in October) | [8 empty] | ✔ | ✔ |  |  | COMPLETED | Engineered AR 3D interactive periodic table with category color coding, orbital shell visualization, and comprehensive element data drawer.
Responsive Flame Test Solution Picker Dialog | [8 empty] | ✔ | ✔ |  |  | COMPLETED | Redesigned solution picker modal matching SciLab aesthetics; resolved RenderFlex overflow issues across landscape and compact mobile screens.
Order-Independent Flexible Ingredient Mixing Engine | [8 empty] | ✔ | ✔ |  |  | COMPLETED | Overhauled reaction logic across Exp 1 to Exp 6 to allow ingredients to be mixed in any order prior to activator addition (preserving strict steps for Exp 7 & 8).
Chemical Safety Hazard Warning Engine (Toxic Gas Modal) | [9 empty] | ✔ |  |  | ACTIVE / POLISHED | Implemented high-visibility safety hazard modal with 'OK' dismissal and instant scene reset upon lethal chemical mixes (e.g., Bleach + Acid -> Cl2 gas).
Universal Light & Dark Mode Theming Across All Views | [8 empty] | ✔ | ✔ |  |  | COMPLETED | Implemented complete dual-theme palette across Student, Teacher, and Web Admin interfaces with dynamic persistent preference caching.